## background
B | Effective date | Name | Training release date | Guidance/Bulletin release date | Notes on progress | Begin plan | Delivery date | Project closes
|  | Medication Administration: Abbreviated | 2019-09-01 |  | Currenly underway |  | 2019-09-01 |  | 1st wk of Sept with field test w/coalition with end product by Oct 2019
|  | Medication Administration: Standard | 2019-12-01 |  | Currenly underway |  | 2019-12-01 |  | Target date completion end of 2019 with voice talent recording - Temple providing suport (inlcudes gender nuetral phrasing, etc)
|  | Human Rights and Restrictive Procedures | 10/1/2019 webinars |  | Ready | 2019-02-04 | 10/1/2019 webinars |  | Completed POD review 8/27/19. Scheduled for October (f2f in spring- March and April)
|  | Claims Documentation |  |  | There is a bulletin update to consider | 2019-08-28 |  |  | FROM BD MEETING 8/28) Per Kristin - Revised bulettin is needed - CMS audit to come - new set of trainngs required
|  | 6100 Orientation Webcast | Upon Promulgation |  | Awaiting Promulgation of Regs - flip the switch to live at that time | 2019-02-04 | Upon Promulgation |  | Delivered to ODP 5/20 - ready to go when regs promulgate - New webcasts: • Individual Rights -https://www.myodp.org/course/view.php?id=1189 • Person Centered Practices -https://www.myodp.org/course/view.php?id=1190 Previous content/already available • Abuse:https://www.myodp.org/course/view.php?id=1187 • Recognizing and Reporting Incidents -https://www.myodp.org/course/view.php?id=1188
|  | QM Plan | 2019-03-18 |  | 100% | 2019-02-04 | 2019-03-18 |  | completed
|  | Community Participation Supports | 6/20/19, 6/24/2019 |  | 100% | 2019-02-04 | 6/20/19, 6/24/2019 |  | This training was to be about newly enrolled service locations not serving more than 25 individuals at any one time that was to become effective March 17, 2019. We were going to deliver this training with the waiver amendments. Since both the waivers and the regulations have been delayed way beyond this date, we had to release guidance instead (19-034 and 19-084). Policy did present on this change during the public comment webinars on June 20th and 24th. I would mark this as 100% complete unless you have notes that this was about something else.
|  | Enforcement | Go To will be scheduled 3 wks after promulgation |  | Ready | 2019-02-04 | Go To will be scheduled 3 wks after promulgation |  | The "Enforcement" training for externals will be identical to the internal version but for a few minor edits, so it can be considered complete.
|  | Reserved Capacity (minus AAW) |  |  | Work in Progress, nearly complete | 2019-02-04 |  |  | POD Review is complete. We need to make a couple of final changes and then it will be ready for when the regulations are published.
|  | Rate Setting |  |  |  | 2019-02-04
|  | Reserved Capacity (including AAW) |  |  | Work in Progress | 2019-02-04 |  |  | And we just wanted to confirm that Amber was able to review the materials and while there is a lot there that we can use, that we will have to have a separate training session for AAW to include whatever process is identified since we still do not have responses on how it will work yet in HCSIS or how it will be paid for. Thanks, Steph
|  | Incident Management | [6 empty] | KA advised on 8/28 at BD meeting - IM must focus on culture of safety - currenty Why We Do It and See Something Say Something - beeds more. Face to face component also needed on Cuture of Safety
6100s Timeline | Delivery date | 6100s Timeline |  | Delivery date
Claims Documentation | 2018-10-01 | Claims Documentation |  | 2018-10-01
Medication Administration | 2018-12-18 | Medication Administration |  | 2018-12-18
QM Plan | 2019-03-18 | QM Plan |  | 2019-03-18
Community Participation Supports | 6/20/19, 6/24/2019 | Community Participation Supports |  | 6/20/19, 6/24/2019
Human Rights and Restrictive Procedures | 2019-10-01 | Human Rights and Restrictive Procedures |  | 2019-10-01
6100 Orientation Webcast | Upon Promulgation Columbus will make live | 6100 Orientation Webcast |  | Upon Promulgation Columbus will make live
Enforcement | Go To will be scheduled 3 wks after promulgation | Enforcement |  | Go To will be scheduled 3 wks after promulgation
Reserved Capacity (minus AAW) | TBA | Reserved Capacity (minus AAW) |  | TBA
Reserved Capacity (including AAW) | TBA | Reserved Capacity (including AAW) |  | TBA
Rate Setting | TBA | Rate Setting |  | TBA
TASKS
| Communication needed to field - should give dates - detail release of overview, then series order with projected dates of delivery (timeline) |  |  | Communication needed to field - should give dates - detail release of overview, then series order with projected dates of delivery (timeline)

## Sheet1
Section Title | Section Number | Section Effective date | Training Topic | Training Release Date | Training Format | Link | Additional Information
Regulatory Package | Entire Package | N/A | ODP Regulation Package Update from Deputy Secretary Ahrens | Three opportunities, please select one: •October 17, 2019 3:00pm to 4:00pm •October 18, 2019 2:00pm to 3:00pm •October 25, 2019 12:00pm to 1:00pm | Live Webcast | https://register.gotowebinar.com/rt/1117462656563198476 | Future ODP communication announcing training
General Provisions | 6100.1-3 | 2019-10-05 | 6100 General Overview and Enforcement | October 30, 2019 10am-11:30am | Live Webcast | Registration Required at the following link: | Future ODP communication announcing training
Transition to a New Provider | 6100.301-307 | 2020-02-01
Medication Administration Training | 6100.468-469 | 2020-02-01
General Payment Provisions | 6100.481-485 | 2019-10-05 |  |  |  | https://register.gotowebinar.com/register/1779236715024150539
Fee Schedule | 6100.571 | 2019-10-05
Cost-Based Rates and Allowable Costs | 6100.641 - 672 | 2019-10-05
Department-Established Fee for Ineligble Portion of Residential Service | 6100.711 | 2020-02-01
Enforcement | 6100.741 - 744 | 2019-10-05
Medication Administration | 6100.461-469 | 2020-02-01 | Medication Administration: Abbreviated | Late October 2019 | Online Course | TBA | Future ODP communication announcing training
|  |  | Medication Administration: Standard | December 2019 | Online Course | TBA | Future ODP communication announcing training
Individual Rights | 6100.181-186 | 2020-02-01 | Rights and Restrictive Procedures Series | Late October 2019 | Webcasts | Content in development | Bulletin 00-18-01 published 4/13/18: Guidelines Concerning Sexual Health, Personal Relationships, and Sexuality available online at:
http://www.dhs.pa.gov/provider/BulletinSearch/bulletinselected/index.htm?bn=00-18-01&o=N&po=ODP&id=04/13/2018
Rights and Restrictive Procedures | 6100.341-350 | 2020-02-01 |  | 2020-03-01 | Face-to-face sessions | Content in development | Future Bulletin: Guidance for the Development of Human Rights Teams and Human Rights Committees
Physical Environment of HCBS (Specific to ID/A Waivers) |  |  | Approved Program Capacity and Noncontiguous Locations |  |  | Registration Required at the following link: | Future ODP communication announcing APC and Noncontiguous Locations Form and Instructions
| 6100.55 | 2019-10-05 |  | October 31, 2019 10:30am to 12:00pm | Live Webcast | https://register.gotowebinar.com/register/1136673323698679564 | Communication 19-034 Requirements Regarding the Number of Individuals Served in Licensed Facilities that Provider Community Participation Support or Day Habilitation Services available online at:
| 441; 444-445 | 2020-02-01 |  |  |  |  | https://www.myodp.org/mod/data/view.php?d=18&perpage=100&search=&sort=415&order=DESC&advanced=0&filter=1&advanced=1&f_420=&f_415_d=3&f_415_m=10&f_415_y=2019&f_417=&f_423=19-034&f_421=&f_418=
Reserved Capacity (Specific to AAW) | 6100.55 | 2019-10-05 | Reserved Capacity | November 2019 | Live Webcast | Content in development | Future ODP communication announcing form and instructions
Orientation | 6100.142 | 2020-02-01 | Professional Provider Staff Orientation • Individual Rights • Person Centered Practices • Prevention, detection and reporting of abuse • Recognizing and Reporting Incidents | 2019-11-01 | Recorded Webcast (Training Modules) | 2019-11-01 | Future ODP communication announcing training
Documentation of Claims and Progress Notes | 6100.226-227 | 2019-10-05 | Claims Documentation and Progress Notes | November/ December 2019 | Live Webcast | Content in development | Bulletin 00-18-04 published 7/25/2018: Interim Technical Guidance for Claim and Service Documentation available online at:
http://www.dhs.pa.gov/provider/BulletinSearch/bulletinselected/index.htm?bn=00-18-04&o=N&po=ODP&id=07/25/2018
Future Bulletin: Technical Guidance for Claim and Service Documentation
Agency With Choice | 6100.801 | Delayed to 2/1/2020 | Agency With Choice | Late November 2019 | Live Webcast | Content in development | Future Bulletin: Participant-Directed Services: Agency with Choice Financial Management Services Model
Quality Management | 6100.45 | 2020-02-01 | Quality Management | Ongoing | Webcast | https://www.myodp.org/course/index.php?categoryid=265 | ODP Communication 19-018: Chapter 6100 Quality Management Planning Requirements for Adult Autism Waiver Supports Coordination Organizations and Providers available online at:
https://s3-us-west-2.amazonaws.com/palms-awss3-repository/Communications/ODP/2019/ODPANN+19-018+ODP+Announces+New+Qality+Management+Requirements+for+AAW+SCOs+Providers.pdf
|  |  |  | Ongoing | Face-to-face QM Certification Course | https://www.myodp.org/course/index.php?categoryid=363 | Bulletin 00-17-01 published 6/20/17: Quality Management Strategy of the Office of Developmental Programs available online at:
http://www.dhs.pa.gov/provider/BulletinSearch/bulletinselected/index.htm?bn=00-17-01&o=N&po=ODP&id=06/20/2017
Incident Management |  |  | Incident Management | TBA |  | TBA | Future Bulletin: Incident Management
| 6100.401-405 | 2020-02-01 |  |  | Webcasts |  | Future Bulletin: Certified Investigations
| 6100.402(c)(2), (c)(3) and (c)(6) | Delayed to January 2021 |  |  | Face-to-face |  | Communication 19-127 Investigations by an ODP-Certified Investigator Required by Chapter 6100: ODP’s Expectations and Implementation Strategy available online at
https://palms-awss3-repository.s3-us-west-2.amazonaws.com/Communications/ODP/2019/ODPANN+19-127+REVISED+Investigations+by+an+ODP-Certified+Investigator+Required+by.pdf
Individual Plan | 6100.221-225 | 2020-02-01 | Individual Plan | N/A | N/A | N/A | Future Individual Support Plan (ISP) Manual
Support coordination, targeted support management and basefunding support coordination | 6100.802 | 2020-02-01 | Application of the Regulations to Supports Coordinators | TBA | Live Webcast | Content in development | Communication 19-127 Investigations by an ODP-Certified Investigator Required by Chapter 6100: ODP’s Expectations and Implementation Strategy available online at:
|  | 6100.802(e) pertaining to incident reporting is delayed to January 2021 |  |  |  |  | https://palms-awss3-repository.s3-us-west-2.amazonaws.com/Communications/ODP/2019/ODPANN+19-127+REVISED+Investigations+by+an+ODP-Certified+Investigator+Required+by.pdf
Organized health care delivery system/ Vendor Goods and Services | 6100.803 and 805 | Delayed to 2/1/2020 | Organized Health Care Delivery System OHCDS/ Vendor Goods and Services | February 2020 | Live Webcast | Content in development | Regulatory Compliance Guide
Room and Board | 6100.681-694 | 2020-02-01 | Applying the Rules of Room and Board | Late January 2020 | Live Webcast | Content in development | Future Bulletin
Communication | 6100.5 | 2020-02-01 | Best Practices When Working With an Interpreter | 2018-12-21 | Recorded Webcasts | https://www.myodp.org/course/view.php?id=1429 | Bulletin 00-14-04 published on 04/08/2014: Accessibility of Intellectual Disability Services for Individuals Who Are Deaf available online at:
|  |  | Deaf Sensitivity Training | 2018-12-07 |  | https://www.myodp.org/course/view.php?id=1448 | http://www.dhs.pa.gov/provider/BulletinSearch/bulletinselected/index.htm?bn=00-14-04&o=N&po=ODP&id=04/08/2014
|  |  | Deaf Space: What Does It Look Like | 2019-01-29 |  | https://www.myodp.org/course/view.php?id=1458
|  |  | Deaf-Blindness 101: Communication and Equal Access | 2019-03-26 |  | https://www.myodp.org/course/view.php?id=1461 | Future Bulletin on Communication
|  |  | Making Homes Accessible for Deaf and Hard of Hearing Individuals | 2019-03-13 |  | https://www.myodp.org/course/view.php?id=1460
|  |  | The Seven Senses and Hand-under-Hand Prompting | 2018-12-14 |  | https://www.myodp.org/course/view.php?id=1430
Appeals and Monitoring Compliance | 6100.41-42 | 2020-02-01 | N/A | N/A | N/A | N/A | Regulatory Compliance Guide
Regulatory Waiver | 6100.43 | 2020-02-01 |  |  |  |  | Future ODP communication announcing the form that will be used for requesting a regulatory waiver.
Innovation Project | 6100.44 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Protective Services; Criminal History Checks; Funding, hiring, retention and utilization; Child abuse history certification | 6100.46-49 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Complaints by an individual, Applicable statutes and regulations, Conflict of interest, Recordkeeping | 6100.51-6100.54 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Children's Services | 6100.56 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Enrollment | 6100.81-85 | 2020-02-01 |  |  |  |  | Future Bulletin: Provider Manual
Training | 6100.141-143 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Community Participation and Employment | 6100.261-262 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Physical Environment of HCBS, Integration | 6100.442 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Base-funding | 6100.804 | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide
Chapters 2380, 2390, 6400 and 6500 | All sections that were revised as part of the regulatory package | 2020-02-01 |  |  |  |  | Regulatory Compliance Guide